## Manual Chart
DLSim Weekly Update
Please go to DLSim Log document and write down your progress, https://docs.google.com/document/d/1GZ8Ov1l3tyWX9RmZLt2VFu-msk91txC25bfjs8p6d-g/edit?usp=sharing
[8 empty] | 2023-04-17 |  |  | 2023-04-21 |  | 2023-04-24 |  |  | 2023-04-28 |  | 2023-05-01 |  |  | 2023-05-05 |  | 2023-05-08 |  |  | 2023-05-12
| TASK NAME | START DATE | END DATE | DUE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4
[8 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
Overall Work Flow
| Work flow document | 2023-04-15 | 2023-04-22 |  | 7 | Fang (Alicia) | 0% | bar: WEEK 1 M to WEEK 1 F
Python Package Development
| Pseudocode | 2023-04-15 | 2023-04-29 |  | 14 | Xiangyong (Roy) | 0% | bar: WEEK 1 M to WEEK 3 M
Build DTALite as shared library and DLL using CMake for DLsim python
| https://github.com/jdlph/DTALite Build DTALite as shared library and DLL using CMake for DLsim python config.h extern "C" DTALIBRARY_API double network_assignment(int assignment_mode, int iteration_number, int column_updating_iterations, int ODME_iterations, int sensitivity_analysis_iterations, int simulation_output, int number_of_memory_blocks); extern "C" DTALIBRARY_API int trace2od(); | TBD | TBD |  |  | Xiangyong (Roy) | 0%
[6 empty] | Xiangyong (Roy) | 0%
[6 empty] | Xiangyong (Roy) | 0%
Add funcitons
| DL.perform_kernel_network_assignment_simulation() | 2023-04-15 | 2023-04-17 |  | 2 | Xiangyong (Roy) | 100% | bar: WEEK 1 M to WEEK 1 T
| settings.csv: view_settings_file, update_settings_file, | 2023-04-18 | 2023-04-22 |  | 2 | Xiangyong (Roy) | 0% | bar: WEEK 1 W to WEEK 1 F
| update_setting_colume_generation_itertions, update_setting_route_based_assignment(true or false),update_setting_simulation(true or false),update_setting_ODME(true or false): measurement file is --> warning, update_setting_sensivitity_analysis(true or false) scenario_analysis.csv | 2023-04-19 | 2023-04-24 |  | 2 | Xiangyong (Roy) | 0% | bar: WEEK 2 M to WEEK 2 W
| DL.check_input_network() macro network, meso network (path4gmns) ->osm2gmns DL.check_input_zone() -> DTALite has built in function to geneate zone.csv or use grid2demand DL.check_input_demand() -> grid2demand DL.check_input_control() -> signal4gmns DL.check_input_connectivity() ->path4mns DL.check_input_traffic_flow_model() ->Data2vdf | 2023-04-25 | 2023-05-01 |  |  |  | 0% | bar: WEEK 2 W to WEEK 3 M
| DL.check_all_input, DL.check_all_output, DL.check_output_summary (pandans) DL.check_output_link_performance DL.check_output_route DL.check_output_trajectory | TBD | TBD
Other Similar Software Pros and Cons
MATSim
| Test and summarize worthwhile fucntions | 2023-04-16 | 2023-04-18 |  | 2 | Yunus | 0% | bar: WEEK 1 T to WEEK 1 W
SUMO
| Test and summarize worthwhile fucntions | 2023-04-18 | 2023-04-20 |  | 2 | Yunus | 0% | bar: WEEK 1 Th to WEEK 1 F
https://github.com/flow-project/flow
| Test and summarize worthwhile fucntions | 2023-04-20 | 2023-04-22 |  | 2 | Yunus | 0% | bar: WEEK 2 M
Test
| Chicago | 2023-04-29 | 2023-04-30 |  | 1 | Yunus | 0% | bar: WEEK 3 M to WEEK 3 T
| DDI | 2023-05-01 | 2023-05-02 |  | 1 | Yunus | 0% | bar: WEEK 3 W to WEEK 3 Th
Users guide
|  | 2023-04-29 | 2023-05-06 |  | 7 | Yunus | 0% | bar: WEEK 3 M to WEEK 4 M